## Assumptions
BaCP - NeurIPS workshop run plan: assumptions
Every blue cell is an input you can change; the Run Plan recalculates from them.
Source of all timing below | docs/research_overview.md sec 4.3 (MEASURED, 4x RTX 5070 Ti, 8 slots)
1 U = one 250-epoch full-length run (seconds) | 2050
Aggregate throughput across 8 slots (U/hour) | 14
GPU cost ($/hour, Vast.ai) | 1.603
Stem-fix wall-clock multiplier (ESTIMATE - see note) | 2.5 | sec 4.5: maxpool->Identity multiplies MACs by 3.98. Wall-clock will rise by less than that (dataloader + overhead). 2.5 is a placeholder - REPLACE with a measured s/epoch after the stem fix.
Per-script cost correction (sec 4.3: the manifest's cost_u understates BaCP by 1.95x)
script | multiplier | basis
baseline | 1 | A0 measured at 2050 s = definition of 1 U (script label is "baseline" in the manifest)
pruning | 0.95 | C0 measured at 1950 s
bacp | 1.95 | C-null measured at 4401 s vs cost_u=1.1 nominal
Config cost factor (relative to resnet34/cifar10)
resnet34/cifar10 = 1.0 ¦ resnet34/cifar100 = 1.0 (same images) ¦ resnet50/cifar10 = 1.4 (est, Bottleneck) ¦ resnet34/svhn = 1.5 (73,257 vs 50,000 train images)
WARNING
All timings above predate the stem fix (sec 4.5) and were taken on 4x RTX 5070 Ti, not an A100. Re-measure s/epoch on one A0 cell before trusting any total.

## Run Plan
# | Phase | Rung | What changes | Question it answers | Model | Dataset | Sparsity | Seeds | Script | cost_u nom | Script mult | Cfg factor | U / seed | Total U | Wall-hrs | Depends on | Gate | Status | Notes
PHASE 0 - Unblock (Thu 20 - Fri 21 Aug). All 8 arms launch as ONE pool. Run is ~33 min; you get the answer in under 2 hours, not 3 days.
2 | PHASE 0 | N1 | C0 as-is, repeat | reproduce the NaN on current code | resnet34 | cifar10 | 0.999 | 1 | pruning | 1 | 0.95 | 1 | 0.95 | 0.95 | 0.16964 | - | - | TODO | -
3 | PHASE 0 | N2 | AMP off (enable_mixed_precision=False) | is fp16 the cause | resnet34 | cifar10 | 0.999 | 1 | pruning | 1 | 0.95 | 1 | 0.95 | 0.95 | 0.16964 | - | - | TODO | trainer.py:44 - AMP is on by default and is not a protocol field
4 | PHASE 0 | N3 | grad clip 1.0 re-enabled | is the unclipped step the cause | resnet34 | cifar10 | 0.999 | 1 | pruning | 1 | 0.95 | 1 | 0.95 | 0.95 | 0.16964 | - | - | TODO | training_utils.py:598 - the call is commented out
5 | PHASE 0 | N4 | pruner moved outside the GradScaler window | is mutating weights between unscale_() and step() the cause | resnet34 | cifar10 | 0.999 | 1 | pruning | 1 | 0.95 | 1 | 0.95 | 0.95 | 0.16964 | - | - | TODO | training_utils.py:505,513-517 - MY PRIMARY SUSPECT
6 | PHASE 0 | N5 | lr 0.1 -> 0.03 | is the LR the cause | resnet34 | cifar10 | 0.999 | 1 | pruning | 1 | 0.95 | 1 | 0.95 | 0.95 | 0.16964 | - | - | TODO | manifest.py:96, no warmup on the cosine branch
7 | PHASE 0 | N6 | 5-epoch linear warmup | is the absence of warmup the cause | resnet34 | cifar10 | 0.999 | 1 | pruning | 1 | 0.95 | 1 | 0.95 | 0.95 | 0.16964 | - | - | TODO | training_utils.py:343-350
8 | PHASE 0 | N7 | AMP off + grad clip 1.0 | belt and braces - does the pair fix it | resnet34 | cifar10 | 0.999 | 1 | pruning | 1 | 0.95 | 1 | 0.95 | 0.95 | 0.16964 | - | - | TODO | confirms if 2+3 interact
9 | PHASE 0 | N8 | sparsity 0.999 -> 0.99 | is this a 0.999-only pathology | resnet34 | cifar10 | 0.999 | 1 | pruning | 1 | 0.95 | 1 | 0.95 | 0.95 | 0.16964 | - | - | TODO | also tells you whether to move the anchor
PHASE 1 - Anchor spine (Sat 22 - Mon 24 Aug). Tier 1 exactly as manifest.py defines it. This is the paper.
11 | PHASE 1 | A0 | no pruning at all | the dense reference | resnet34 | cifar10 | 0.999 | 5 | baseline | 1 | 1 | 1 | 1 | 5 | 0.89286 | - | - | TODO | 5 seeds, zero NaN so far: 91.64 +- 0.30. VOID as a final number until the stem fix.
12 | PHASE 1 | A2 | uniform magnitude, head dense | does excluding the classifier matter | resnet34 | cifar10 | 0.999 | 5 | pruning | 1 | 0.95 | 1 | 0.95 | 4.75 | 0.84821 | A0 | - | TODO | Magnitude has never run at 0.999 - sec 7.9.
13 | PHASE 1 | A3 | ERK layer-wise budget | does ERK beat uniform | resnet34 | cifar10 | 0.999 | 5 | pruning | 1 | 0.95 | 1 | 0.95 | 4.75 | 0.84821 | A0 | - | TODO | Implements ER-on-unrolled, not Evci's ERK - flag F8, sec 8.3a. Re-word the citation or fix the mass.
14 | PHASE 1 | A4 | ERK + head dense | closes the 2x2 | resnet34 | cifar10 | 0.999 | 5 | pruning | 1 | 0.95 | 1 | 0.95 | 4.75 | 0.84821 | A0 | - | TODO
15 | PHASE 1 | A5 | + RigL drop-and-regrow | does dynamic topology beat a static mask | resnet34 | cifar10 | 0.999 | 5 | pruning | 1 | 0.95 | 1 | 0.95 | 4.75 | 0.84821 | A0 | - | TODO | The ONLY pruner exercised at scale so far.
16 | PHASE 1 | C-null | BaCP code path, everything BaCP-specific off | is the BaCP code path neutral | resnet34 | cifar10 | 0.999 | 5 | bacp | 1.1 | 1.95 | 1 | 2.145 | 10.725 | 1.9152 | A0 | G1 | TODO | Cheapest, highest-information run in the plan. 5/5 seeds NaN on the last attempt.
17 | PHASE 1 | C0 | plain supervised training on the winning substrate | THE reference every later rung is measured against | resnet34 | cifar10 | 0.999 | 5 | pruning | 1 | 0.95 | 1 | 0.95 | 4.75 | 0.84821 | A0 | - | TODO | The arm the AAAI paper had no analogue of.
18 | PHASE 1 | C0b | two augmented views per step, objective unchanged | is a gain contrast, or just more augmentation | resnet34 | cifar10 | 0.999 | 5 | bacp | 1.4 | 1.95 | 1 | 2.73 | 13.65 | 2.4375 | C-null | - | TODO | Not optional. Without it 'contrast helps' and 'two views help' are not separable.
19 | PHASE 1 | C1 | + dense-teacher logit KD | does A TEACHER help at all | resnet34 | cifar10 | 0.999 | 5 | bacp | 1.6 | 1.95 | 1 | 3.12 | 15.6 | 2.7857 | C0b | G3 | TODO | THE decider. If C1 ~= D2 the contrastive machinery is decoration.
20 | PHASE 1 | C2 | logit KD -> feature matching | does the LEVEL of injection matter | resnet34 | cifar10 | 0.999 | 5 | bacp | 1.6 | 1.95 | 1 | 3.12 | 15.6 | 2.7857 | C1 | G3 | TODO
21 | PHASE 1 | C3 | feature regression -> contrastive form (FiC) | does the CONTRASTIVE FORM matter | resnet34 | cifar10 | 0.999 | 5 | bacp | 1.8 | 1.95 | 1 | 3.51 | 17.55 | 3.1339 | C2 | G4 | TODO | BROKEN AS SPECIFIED - supervised=True adds label positives AND the denominator. See Blockers B6.
22 | PHASE 1 | D1 | + SnC snapshot teachers | does SnC add anything on top of FiC | resnet34 | cifar10 | 0.999 | 5 | bacp | 2 | 1.95 | 1 | 3.9 | 19.5 | 3.4821 | C3 | G5 | TODO
23 | PHASE 1 | D2 | + PrC pretrained teacher = FULL BaCP | does PrC add anything on top of FiC+SnC | resnet34 | cifar10 | 0.999 | 5 | bacp | 2.2 | 1.95 | 1 | 4.29 | 21.45 | 3.8304 | D1 | G5 | TODO | PrC's teacher is RANDOMLY INITIALISED on this box. See Blockers B2 - this changes what D2 means.
PHASE 2 - Transfer panel (Mon 24 - Tue 25 Aug). Four rungs only, two seeds. This is how you get breadth back without re-running the ladder.
25 | PHASE 2 | A0 | dense reference for this cell | anchor for the panel | resnet34 | cifar100 | 0.999 | 2 | baseline | 1 | 1 | 1 | 1 | 2 | 0.35714 | - | - | TODO | 2nd dataset, free - same images, same loaders, transform path already works
26 | PHASE 2 | C0 | CE only | the reference | resnet34 | cifar100 | 0.999 | 2 | pruning | 1 | 0.95 | 1 | 0.95 | 1.9 | 0.33929 | A0 | - | TODO | Transfer panel - report as n=2, no significance claim.
27 | PHASE 2 | C1 | + dense-teacher logit KD | does a teacher help here too | resnet34 | cifar100 | 0.999 | 2 | bacp | 1.6 | 1.95 | 1 | 3.12 | 6.24 | 1.1143 | C0 | - | TODO | Transfer panel - report as n=2, no significance claim.
28 | PHASE 2 | C3 | contrastive form (FiC) | does contrast beat KD here too | resnet34 | cifar100 | 0.999 | 2 | bacp | 1.8 | 1.95 | 1 | 3.51 | 7.02 | 1.2536 | C1 | - | TODO | Transfer panel - report as n=2, no significance claim.
29 | PHASE 2 | D2 | full BaCP | does the full method hold up | resnet34 | cifar100 | 0.999 | 2 | bacp | 2.2 | 1.95 | 1 | 4.29 | 8.58 | 1.5321 | C3 | - | TODO | Transfer panel - report as n=2, no significance claim.
30 | PHASE 2 | A0 | dense reference for this cell | anchor for the panel | resnet50 | cifar10 | 0.999 | 2 | baseline | 1 | 1 | 1.4 | 1.4 | 2.8 | 0.5 | - | - | TODO | 2nd model - registered, CIFAR stem adaptation runs for model_family=='resnet'
31 | PHASE 2 | C0 | CE only | the reference | resnet50 | cifar10 | 0.999 | 2 | pruning | 1 | 0.95 | 1.4 | 1.33 | 2.66 | 0.475 | A0 | - | TODO | Transfer panel - report as n=2, no significance claim.
32 | PHASE 2 | C1 | + dense-teacher logit KD | does a teacher help here too | resnet50 | cifar10 | 0.999 | 2 | bacp | 1.6 | 1.95 | 1.4 | 4.368 | 8.736 | 1.56 | C0 | - | TODO | Transfer panel - report as n=2, no significance claim.
33 | PHASE 2 | C3 | contrastive form (FiC) | does contrast beat KD here too | resnet50 | cifar10 | 0.999 | 2 | bacp | 1.8 | 1.95 | 1.4 | 4.914 | 9.828 | 1.755 | C1 | - | TODO | Transfer panel - report as n=2, no significance claim.
34 | PHASE 2 | D2 | full BaCP | does the full method hold up | resnet50 | cifar10 | 0.999 | 2 | bacp | 2.2 | 1.95 | 1.4 | 6.006 | 12.012 | 2.145 | C3 | - | TODO | Transfer panel - report as n=2, no significance claim.
35 | PHASE 2 | A0 | dense reference for this cell | anchor for the panel | resnet34 | svhn | 0.999 | 2 | baseline | 1 | 1 | 1.5 | 1.5 | 3 | 0.53571 | - | - | TODO | 3rd dataset - registered, 32x32, never run
36 | PHASE 2 | C0 | CE only | the reference | resnet34 | svhn | 0.999 | 2 | pruning | 1 | 0.95 | 1.5 | 1.425 | 2.85 | 0.50893 | A0 | - | TODO | Transfer panel - report as n=2, no significance claim.
37 | PHASE 2 | C1 | + dense-teacher logit KD | does a teacher help here too | resnet34 | svhn | 0.999 | 2 | bacp | 1.6 | 1.95 | 1.5 | 4.68 | 9.36 | 1.6714 | C0 | - | TODO | Transfer panel - report as n=2, no significance claim.
38 | PHASE 2 | C3 | contrastive form (FiC) | does contrast beat KD here too | resnet34 | svhn | 0.999 | 2 | bacp | 1.8 | 1.95 | 1.5 | 5.265 | 10.53 | 1.8804 | C1 | - | TODO | Transfer panel - report as n=2, no significance claim.
39 | PHASE 2 | D2 | full BaCP | does the full method hold up | resnet34 | svhn | 0.999 | 2 | bacp | 2.2 | 1.95 | 1.5 | 6.435 | 12.87 | 2.2982 | C3 | - | TODO | Transfer panel - report as n=2, no significance claim.
PHASE 3 - Only if Phases 0-2 are done by Tue 25 Aug. Otherwise cut without regret.
41 | PHASE 3 | D4-noSnC | SnC removed, weights renormalised to 1/3 | is SnC necessary (backward) | resnet34 | cifar10 | 0.999 | 5 | bacp | 2.2 | 1.95 | 1 | 4.29 | 21.45 | 3.8304 | D2 | - | STRETCH | Keep - has no forward twin, so the gap is informative.
42 | PHASE 3 | D4-noFiC | FiC removed, weights renormalised to 1/3 | is FiC necessary (backward) | resnet34 | cifar10 | 0.999 | 5 | bacp | 2.2 | 1.95 | 1 | 4.29 | 21.45 | 3.8304 | D2 | - | STRETCH | Keep - has no forward twin.
43 | PHASE 3 | C0 @0.95 | same rung at a lower sparsity | the accuracy-vs-sparsity trend all three reviewers asked for | resnet34 | cifar10 | 0.95 | 2 | pruning | 1 | 0.95 | 1 | 0.95 | 1.9 | 0.33929 | Phase 1 | - | STRETCH | HEADLINE_SPARSITIES is declared in manifest.py:69 and wired to nothing - needs a driver (sec 8.8).
44 | PHASE 3 | C1 @0.95 | same rung at a lower sparsity | the accuracy-vs-sparsity trend all three reviewers asked for | resnet34 | cifar10 | 0.95 | 2 | bacp | 1.6 | 1.95 | 1 | 3.12 | 6.24 | 1.1143 | Phase 1 | - | STRETCH | HEADLINE_SPARSITIES is declared in manifest.py:69 and wired to nothing - needs a driver (sec 8.8).
45 | PHASE 3 | C3 @0.95 | same rung at a lower sparsity | the accuracy-vs-sparsity trend all three reviewers asked for | resnet34 | cifar10 | 0.95 | 2 | bacp | 1.8 | 1.95 | 1 | 3.51 | 7.02 | 1.2536 | Phase 1 | - | STRETCH | HEADLINE_SPARSITIES is declared in manifest.py:69 and wired to nothing - needs a driver (sec 8.8).
46 | PHASE 3 | D2 @0.95 | same rung at a lower sparsity | the accuracy-vs-sparsity trend all three reviewers asked for | resnet34 | cifar10 | 0.95 | 2 | bacp | 2.2 | 1.95 | 1 | 4.29 | 8.58 | 1.5321 | Phase 1 | - | STRETCH | HEADLINE_SPARSITIES is declared in manifest.py:69 and wired to nothing - needs a driver (sec 8.8).
47 | PHASE 3 | C0 @0.99 | same rung at a lower sparsity | the accuracy-vs-sparsity trend all three reviewers asked for | resnet34 | cifar10 | 0.99 | 2 | pruning | 1 | 0.95 | 1 | 0.95 | 1.9 | 0.33929 | Phase 1 | - | STRETCH | HEADLINE_SPARSITIES is declared in manifest.py:69 and wired to nothing - needs a driver (sec 8.8).
48 | PHASE 3 | C1 @0.99 | same rung at a lower sparsity | the accuracy-vs-sparsity trend all three reviewers asked for | resnet34 | cifar10 | 0.99 | 2 | bacp | 1.6 | 1.95 | 1 | 3.12 | 6.24 | 1.1143 | Phase 1 | - | STRETCH | HEADLINE_SPARSITIES is declared in manifest.py:69 and wired to nothing - needs a driver (sec 8.8).
49 | PHASE 3 | C3 @0.99 | same rung at a lower sparsity | the accuracy-vs-sparsity trend all three reviewers asked for | resnet34 | cifar10 | 0.99 | 2 | bacp | 1.8 | 1.95 | 1 | 3.51 | 7.02 | 1.2536 | Phase 1 | - | STRETCH | HEADLINE_SPARSITIES is declared in manifest.py:69 and wired to nothing - needs a driver (sec 8.8).
50 | PHASE 3 | D2 @0.99 | same rung at a lower sparsity | the accuracy-vs-sparsity trend all three reviewers asked for | resnet34 | cifar10 | 0.99 | 2 | bacp | 2.2 | 1.95 | 1 | 4.29 | 8.58 | 1.5321 | Phase 1 | - | STRETCH | HEADLINE_SPARSITIES is declared in manifest.py:69 and wired to nothing - needs a driver (sec 8.8).
CUT - decided, not forgotten. Zero seeds so these cost nothing. Each row says what claim you are giving up.
52 | CUT | B1 | DyReLU | - | resnet34 | cifar10 | - | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | - | - | CUT | Defect M5: 3.18M DyReLU params stay in the forward pass and OUTSIDE the sparsity denominator - 150x the surviving weights. Also a different paper.
53 | CUT | B2 | DyReLU phasing | - | resnet34 | cifar10 | - | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | - | - | CUT | Same. Stage B is 'what substrate survives 99.9%', which is not this paper's question.
54 | CUT | B3 | weight sharing | - | resnet34 | cifar10 | - | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | - | - | CUT | Same.
55 | CUT | D4-noPrC | leave-one-out PrC | - | resnet34 | cifar10 | - | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | - | - | CUT | Defect: D4-noPrC IS D1 (sec 8.8). The PrC row is zero by construction, not by measurement. Report the D1-D2 contrast in both columns.
56 | CUT | D4-noCE | leave-one-out CE | - | resnet34 | cifar10 | - | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | - | - | CUT | Low information: 'no CE' is not a competing explanation anyone will raise.
57 | CUT | - | ViT-Tiny / ViT-Small | - | vit-tiny | cifar10 | - | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | - | - | CUT | Requires image_size=224 (49x the pixels), hub download, never run under current code. Not in 9 days.
58 | CUT | - | VGG-11 / VGG-19 | - | vgg11 | cifar10 | - | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | - | - | CUT | Defects M2 + M6. Under M2 a '99% sparse VGG-11' leaves 119.5M dense params - 92.8% of the network. Your old VGG rows never tested what they claimed.
59 | CUT | - | WikiText-2 MLM | - | roberta-base-mlm | wikitext2 | - | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | - | - | CUT | Defect D1: load_mlm_dataloaders raises TypeError on seed=, then NameError. Unreachable today.
60 | CUT | - | SST-2 text cell | - | distilbert | sst2 | - | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | - | - | CUT | Reachable (GLUE cache present) but no protocol is defined and testloader IS valloader. Only if Phase 2 finishes early.
61 | CUT | - | ImageNet | - | resnet50 | imagenet | - | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | - | - | CUT | Defect D3: download=True raises on torchvision.datasets.ImageNet. Also not affordable. State as a limitation.
TOTALS
|  |  | Phase 0 (unblock) | [10 empty] | 7.6 | 1.3571
|  |  | Phase 1 (anchor spine) | [10 empty] | 142.825 | 25.5045
|  |  | Phase 2 (transfer panel) | [10 empty] | 100.386 | 17.9261
|  |  | Phase 3 (stretch) | [10 empty] | 90.38 | 16.1393
|  |  | TOTAL (all phases) | [10 empty] | 341.191 | 60.927
|  |  | Estimated GPU cost ($) | [11 empty] | 97.6659
Wall-hrs assumes 8 concurrent slots (2 cells/GPU x 4 GPUs, sec 4.2). Divide differently if you move to a single A100.
Compute was never your constraint. Debugging time is. Phase 0 exists to convert an open-ended debug into a 2-hour experiment.

## Blockers
ID | Defect | Severity | Why it blocks | Fix | Must land by | Status | Note
B1 (sec 8.1) | Sparse training diverges to NaN at 0.999. 5/5 C-null seeds, 2/3 C0 seeds, sitting at exactly 10.0969% (chance). Cause NOT established. | BLOCKER | Nothing can be measured until this is fixed. Every sparse number you have is a dead run. | Phase 0: 8-arm pool, ~2 hours | Thu 20 Aug | OPEN | Do not debug this by reading code. You have 8 slots and a 33-min run. Launch all 8 hypotheses at once.
B2 - NEW FINDING | PrC's teacher is a RANDOMLY INITIALISED network. Every local vision weight path points at /dbfs (model_factory.py MODELS table), which does not exist on the Vast.ai box, so load_weights fails soft and init_source='random' (sec 1.1). bacp.py:488 then contrasts the student against model_pt(data2). | BLOCKER | D2 (= full BaCP) is currently testing 'does aligning to a random network help', not 'does pretrained knowledge help'. The paper's stated rationale for PrC - task-agnostic knowledge from pretraining - is not what the code does. This is not in your 245KB audit: 'model_pt' appears nowhere in research_overview.md. | Decide one of three: (a) load torchvision ImageNet weights for model_pt, (b) drop PrC and publish D1 as the endpoint, (c) keep it and reframe PrC honestly as a random-anchor regulariser | Thu 20 Aug | OPEN | (a) breaks the from-scratch comparability with RigL/GraNet that the anchor was chosen for. (b) is cleanest for 9 days. (c) is the most interesting paper but needs its own control.
B3 (sec 8.7 D4) | The contrastive path builds no validation split, so BaCP trains on 50,000 CIFAR-10 images while the CE baseline gets 40,000. | BLOCKER | A 25% training-data advantage sits on the headline comparison. C0 vs D2 is uninterpretable until this is fixed. Your doc marks it 'open, by design' - I disagree; 'we state it in the paper' does not survive review. | Give the contrastive path the same 40k/10k split | Fri 21 Aug | OPEN | Must land before Phase 1 launches, not after.
B4 (sec 8.2) | Gates G1/G3/G4/G5 are all difference-based with no collapse floor. Two arms both dead at 10.0969% give ¦0.00¦ <= 0.5 and report PASS. | BLOCKER | The gate that exists to prove the BaCP code path is neutral cannot tell 'identical' from 'identically broken'. This is the state your first tier-1 attempt was actually in. | ~10 lines: require both arms > 100/num_classes + k*sigma, plus a NaN-loss check off the record | Fri 21 Aug | OPEN | test_metrics_are_in_range already fails a NaN metric but only runs under pytest -m results, so it does not gate the sweep.
B5 (sec 1.3.3 / M1) | The CIFAR stem keeps its maxpool, so a 32x32 input reaches layer4 at 2x2. MACs are 3.98x too low. Final stage = 61.6% of the backbone, operating on four spatial positions. | HIGH | Invalidates A0 as a final number and every timing in sec 4.3-4.4. Fix decided, not applied. | maxpool -> Identity. Zero params and zero state_dict keys change, so all checkpoints stay loadable. | Fri 21 Aug | OPEN | Re-measure s/epoch immediately after and update Assumptions!B8, which is currently a guess.
B6 (sec 8.3b) | C3 does not isolate one thing. CAPContrastiveLoss is built with supervised=True AND unsupervised=True, so C3 adds the log-sum-exp denominator AND label-defined positives that C2 has no analogue of. | HIGH | This is the exact error the ladder exists to prevent, and it sits on gate G4 and on the paper's central claim. | Run C3 with supervised=False, or insert a C3a rung between C2 and C3 | Fri 21 Aug | OPEN | Cheapest fix is supervised=False - it keeps the rung count and makes C2->C3 genuinely one change (negatives).
B7 (sec 8.8) | D4-noPrC IS D1. They differ in exactly one key, experiment_type, which has no effect on training. | HIGH | The PrC row of the forward/backward table is zero by construction, not by measurement. Also 5 cells x 2.2 U of duplicated compute. | Drop the arm; report the D1-D2 contrast in both columns | Fri 21 Aug | CUT IN PLAN | Already cut on the Run Plan tab.
B8 (sec 8.5) | No gradient clipping anywhere. clip_grad_norm_ appears once, commented out (training_utils.py:598). No max_grad_norm on any config or RunRecord. | HIGH | A contributing fact to B1, combined with lr 0.1, no warmup, fp16 AMP on by default, and a pruner mutating weights inside the GradScaler window. | Arms N3 and N7 of the Phase 0 sweep test it | Thu 20 Aug | OPEN | Re-enabling it is a hypothesis to test, not a fix to announce.
B9 (sec 8.4) | resolve_checkpoint filters on status/model/dataset/method/seed only. No code_fingerprint check, no git_sha, no protocol fields. Falls back to seed=None automatically with only a printed warning. | HIGH | A sparse run will start from a dense checkpoint built by different source code, and every paired CI computed from that rung is overstated. Silent by construction. | Compare code_fingerprint inside resolve_checkpoint; make the seed fallback opt-in | Sat 22 Aug | OPEN | require_gate already does this exact check elsewhere in the same file - copy it.
B10 (sec 8.8) | Welch intervals use a hardcoded t=2.0 when scipy is absent. At df 4-8 the true values are 2.78 and 2.31. | MEDIUM | Unpaired Stage A intervals print up to ~28% too narrow with no warning. scipy is in requirements-dev.txt but not requirements.txt. | pip install scipy on the run box | Sat 22 Aug | OPEN | One command. Do it in the same session as the stem fix.
B11 (sec 3.4 / 8.8) | HEADLINE_SPARSITIES is defined in manifest.py:69 and referenced nowhere. cells() accepts sparsity= but no caller passes it. TIERS[3] claims tier 3 includes the sweep; it does not. | MEDIUM | The accuracy-vs-sparsity trend that all three human reviewers asked for cannot currently be produced. | Write the driver that passes sparsity= through pool.py | Sun 24 Aug | OPEN | Phase 3 on the Run Plan depends on this.
B12 (sec 8.8) | The learnable-lambda arm is not constrained to the simplex. _initialize_lambdas unpacks the tuple with no projection or softmax; the four values are free nn.Parameters. | MEDIUM | Any claim that this arm optimises over the simplex is unsupported by the code. Your appendix Table 5 was going to make exactly that claim. | Drop the dynamic-lambda claim from this paper, or add a softmax | Mon 25 Aug | OPEN | Cheapest: drop it. Reviewers called the method too complex; a fifth knob does not help.
B13 (sec 4.1) | No TF32 policy is set anywhere and the NVIDIA driver version is not recorded. | MEDIUM | Blocks the reproducibility statement. Matmul/conv precision is inherited from whatever torch defaults to on Blackwell. | set_float32_matmul_precision explicitly; add driver to results.py:205-212 | Wed 26 Aug | OPEN | Do it while writing, not before.
B14 (sec 8.6 M2) | _EXCLUDE_TASK_HEAD contains the bare substring 'classifier', so VGG's whole 119.5M MLP leaves the pruning denominator. A '99% sparse VGG-11' leaves 92.8% of the network dense. | MEDIUM | Explains why your AAAI VGG rows behaved oddly - they never pruned what the table said. Only matters if VGG comes back. | Exact-match the final layer instead of substring | Not this deadline | CUT | Worth a line in the paper's limitations if you mention the old VGG results at all.
B15 (sec 8.7 D1) | load_mlm_dataloaders takes no seed parameter but load_text_dataloaders calls it with seed=seed -> TypeError; the nested loader() closure then references a module global that does not exist -> NameError. | MEDIUM | WikiText-2 is unreachable. The MLM half of your AAAI table had no runnable code path. | ~5 lines, but then you still need an MLM protocol | Not this deadline | CUT | Drop all LM claims from the workshop paper.

## Scope
Item | Decision | Status | Why | What it costs you
Anchor model | resnet34 ONLY at 5 seeds | IN | Deep on one cell beats one seed across twelve. A reviewer attacks the claim, not the breadth. | -
2nd model | resnet50, 4-rung panel, 2 seeds | IN (Phase 2) | Registered, same family, CIFAR stem path already runs for model_family=='resnet'. ~11 U. | Answers 'only one architecture' without re-running the ladder.
2nd/3rd dataset | cifar100 + svhn, 4-rung panel, 2 seeds | IN (Phase 2) | Both registered and 32x32. cifar100 is free - identical loaders. ~24 U combined. | Answers 'only one dataset'.
Sparsity trend | 0.95 / 0.99 on C0,C1,C3,D2 | STRETCH (Phase 3) | All three human reviewers asked for trends across pruning rates. Needs the B11 driver first. | This is the single highest-value stretch item.
Anchor sparsity | move from 0.999 to 0.99 | DECIDE FRI | At 0.999 a ResNet-34 is ~21,265 weights. Comparable to CAP (97%), to your own prior table (99%), and to the literature only at 0.99. | N8 of the Phase 0 sweep also tells you whether 0.999 is where the NaN lives.
Stage B (DyReLU, phasing, weight sharing) | OUT | CUT | Defect M5 on B1, and it is a different paper: 'what substrate survives extreme sparsity' is not 'does contrast beat KD'. | You lose the EAST-composition claim. It was unsupported anyway (sec 7.10: every pre-fix EAST number is void).
ViTs | OUT | CUT | image_size=224 is 49x the pixels, hub download, never run under current code. | You lose 'model-agnostic across CNNs and ViTs'. It is already unsupported - sec 1.7.
VGG | OUT | CUT | Defects M2 + M6. The pruning denominator excludes 92.8% of VGG-11. | You lose the architecture where BaCP LOST anyway (0/9 on VGG-11/CIFAR-100 in the old table).
Language models | OUT | CUT | WikiText-2 unreachable (D1). SST-2 reachable but has no protocol and testloader IS valloader. | You lose the cross-modality claim. Say so in Limitations; CAP owns NLP and you can cite that.
ImageNet | OUT | CUT | Defect D3, and not affordable regardless. | Two reviewers asked for it. State it as a limitation with a number: one ResNet-50 cell is ~2.5 days on one card.
Pruning-criterion-agnostic claim | OUT | CUT | Only RigL has ever run at scale. Magnitude, SNIP, WANDA and EAST are untested at these sparsities (sec 7.9). | This was one of your five claimed deltas over CAP. It cannot be re-established by the 29th.
Dynamic / learnable lambdas | OUT | CUT | Not constrained to the simplex (B12), so the claim is unsupported by the code. | Reviewers said the method was too complex. Removing a knob is a feature.
Framing | Lead with the control, not the method | IN | 'Does contrastive teacher alignment beat plain distillation at extreme sparsity? A controlled decomposition.' C1 is the contribution; D2 is the endpoint of the ladder, not the thesis. | Survives a null result. 'BaCP beats I.P. by 2%' does not.

## Reviewer map
Reviewer | Complaint | Where it is answered now | Status | Note
ZzNq (3, conf 4) | No ablations isolating each loss term | Phase 1 C1/C2/C3/D1/D2 forward + Phase 3 D4 backward | COVERED | The ladder is a stronger answer than the leave-one-out table they asked for.
ZzNq | How many snapshots, how spaced, what if you vary the count | num_snapshots=2 is fixed; no K sweep is scheduled | NOT COVERED | One sentence in the paper stating K=2 and why. A K sweep does not fit in 9 days.
ZzNq | Extra cost per batch from multiple teachers - wall time | sec 4.3 has it MEASURED: dense 8.2 s/ep, CE-only 7.8, BaCP 16.3. 1.95x correction. | COVERED | Re-measure after the stem fix, then this is a table you already own. Most papers cannot produce it.
ZzNq | Results only at extreme rates; want trends across sparsity | Phase 3 sparsity sweep | AT RISK | Depends on B11. If it slips, say explicitly that you report one sparsity and why.
KQsH (5, conf 3) | No ImageNet-scale study | Cut | NOT COVERED - BY DECISION | State the limitation with the compute number attached. Workshop reviewers accept a scoped claim.
KQsH | GPU type, training/inference time not stated | sec 4.1 + 4.3 | COVERED | You will have a better hardware section than most accepted papers.
KQsH | How is text augmented for LMs | Cut with the LM cells | N/A | But note sec 2.9's answer is good: in CAP the two views are the same tokens through two different models. Keep that framing if LMs ever return.
KQsH | Bold the row-wise best numbers | ladder.aggregate() + the noise-floor bolding rule (sec 5.10) | COVERED | You have a principled bolding rule now, which is better than what they asked for.
C5T6 (3, conf 4) | Framework overly complex, ablations missing | Phase 1 | COVERED for ablations - BUT the scope grew | Cutting Stage B and D4-noPrC/noCE is what actually answers 'too complex'.
C5T6 | Method underperforms on VGG-11 and VGG-19 | VGG cut - and defect M2 means those rows never pruned what they claimed | EXPLAINED, NOT FIXED | Worth one honest sentence if you reference the old results at all.
C5T6 | No results across random seeds | Phase 1 at 5 seeds; Phase 2 at 2 seeds | COVERED | Report Phase 2 as n=2 with no significance claim. Do not let it look like the anchor.
C5T6 | Effect of data augmentation; add augmentation to the baseline for fairness | C0b is exactly this arm | COVERED - AND IT IS THE BEST THING YOU HAVE | C0b separates 'contrast helps' from 'two views help'. No prior BaCP-like paper runs it.
C5T6 | Source code URL inaccessible | Repo housekeeping | TODO | Trivial and it cost you credibility with a reviewer. Fix it before submission.
AI review | Algorithm 1 inconsistencies, missing hyperparameters | docs/research_overview.md sec 7 + the manifest as the single source of config | COVERED | Generate the hyperparameter table from cells() rather than typing it.
AI review | Table anomalies - duplicated blocks, pruned exceeding dense | All AAAI numbers are VOID (drop_last eval defect, EAST masks never updating) | MOOT - AND SERIOUS | You cannot resubmit that table. Verified independently: ViT-Tiny/C100 and ViT-Small/C10 are identical in 17 of 18 entries.
AI review | Novelty vs CAP is thin - snapshot self-consistency is the only delta | sec 6.7 already drafts the honest paragraph | COVERED IF YOU SHIP IT | Your sec 6.7 is better than most published related-work sections. Put it in the paper in the future tense it is already written in.
AI review | Missing baselines: RigL, movement pruning, CAP | RigL IS your substrate now (A5). CAP is the contrastive_mode. Movement pruning is out. | PARTLY COVERED | RigL-as-substrate is a stronger answer than RigL-as-baseline. Say that explicitly.
AI review | No perplexity for MLM despite claiming it | LM cells cut | N/A | Also: RoBERTa/DistilBERT are encoder-only, not decoder-only as your appendix says. Fix if any LM text survives.